## ProjectSchedule
Travel Sphere: Smart Travel & Community Platform
UCS503 Software Engineering - Software Engineering Project |  |  | Project Start: |  | Wed, 8-12-2026
Team: Niharika ¦ Ayush ¦ Sarwar |  |  | Target Completion: |  | Sun, 11-15-2026
Project: Travel Sphere — Smart Travel & Community Platform |  |  | Duration: |  | 96 Days (Aug 12 – Nov 15, 2026)
[5 empty] | Aug 12 | [6 empty] | Aug 19 | [6 empty] | Aug 26 | [6 empty] | Sep 2 | [6 empty] | Sep 9 | [6 empty] | Sep 16 | [6 empty] | Sep 23 | [6 empty] | Sep 30 | [6 empty] | Oct 7 | [6 empty] | Oct 14 | [6 empty] | Oct 21 | [6 empty] | Oct 28 | [6 empty] | Nov 4 | [6 empty] | Nov 11
[5 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TASK | ASSIGNED TO | PROGRESS | START | END
Phase 1: Inception & Proposal Setup
1. Problem Definition, Motivation & Scope | Sarwar | 100% | 8-12-26 | 8-21-26 | bar: Aug 12 12 W to Aug 19 21 F; Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
2. Initial Project Proposal | Sarwar | 100% | 8-12-26 | 8-25-26 | bar: Aug 12 12 W to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
3. Project Presentation & Pitch Deck | Niharika | 100% | 8-18-26 | 8-28-26 | bar: Aug 12 18 T to Aug 26 28 F; Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
4. GitHub Repository & Team Workflow | Niharika | 100% | 8-22-26 | 8-30-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
Phase 2: System Analysis & Design
5. Requirements & MVP Definition | Sarwar | 100% | 8-26-26 | 9-4-26 | bar: Aug 26 26 W to Sep 2 4 F; Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
6. Use Case Diagram | Sarwar | 100% | 8-28-26 | 9-6-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
7. DFD Level 0 & Level 1 | Sarwar + Niharika | 100% | 9-1-26 | 9-10-26 | bar: Aug 26 1 T to Sep 9 10 T; Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
8. DFD Level 2 | Sarwar | 90% | 9-5-26 | 9-14-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
9. System Architecture | Niharika + Sarwar | 90% | 9-8-26 | 9-18-26 | bar: Sep 2 8 T to Sep 16 18 F; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
10. Database / ER Design | Ayush + Sarwar | 75% | 9-10-26 | 9-20-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
Phase 3: Backend & Core Development
11. Backend Development Environment Setup | Ayush | 100% | 9-5-26 | 9-12-26 | bar: Sep 2 5 S to Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
12. FastAPI Application Setup | Ayush | 100% | 9-10-26 | 9-18-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
13. PostgreSQL & SQLAlchemy Integration | Ayush | 100% | 9-14-26 | 9-23-26 | bar: Sep 9 12 S; Sep 9 14 M to Sep 23 23 W; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
14. Alembic Database Migration Setup | Ayush | 70% | 9-18-26 | 9-28-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
15. User Model & Authentication Backend | Ayush + Sarwar | 0% | 9-22-26 | 10-5-26 | bar: Sep 9 12 S; Sep 16 20 S; Sep 16 22 T to Sep 30 5 M; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
16. API Endpoint Development | Ayush + Sarwar | 0% | 9-28-26 | 10-12-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
17. Backend Service / CRUD Implementation | Sarwar | 0% | 10-5-26 | 10-18-26 | bar: Sep 9 12 S; Sep 16 20 S; Sep 30 5 M to Oct 14 18 S
18. API Testing & Debugging | Ayush + Sarwar | 0% | 10-14-26 | 10-25-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
Phase 4: Frontend & System Integration
19. React Frontend Development | Niharika | 60% | 9-14-26 | 10-5-26 | bar: Sep 9 12 S; Sep 9 14 M to Sep 30 5 M; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S
20. React Component Structure | Niharika | 60% | 9-20-26 | 10-10-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
21. Frontend–FastAPI Integration | Niharika + Ayush | 25% | 10-5-26 | 10-18-26 | bar: Sep 9 12 S; Sep 16 20 S; Sep 30 5 M to Oct 14 18 S
22. API Integration & Data Handling | Niharika + Sarwar | 15% | 10-10-26 | 10-22-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
23. Travel Sphere Core Features | All | 10% | 10-15-26 | 10-30-26 | bar: Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 15 T to Oct 28 30 F
24. Prototype Integration Milestone | All | 0% | 10-26-26 | 11-5-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
Phase 5: Testing, Deployment & Final Delivery
25. Backend & API Testing | Ayush + Sarwar | 0% | 10-26-26 | 11-5-26 | bar: Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S; Oct 21 26 M to Nov 4 5 T
26. Frontend Testing | Niharika | 0% | 10-28-26 | 11-6-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Nov 4 6 F; Nov 4 9 M to Nov 11 13 F
27. End-to-End Integration Testing | All | 0% | 11-1-26 | 11-8-26 | bar: Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S; Oct 28 1 S to Nov 4 8 S
28. Bug Fixing & UI Polishing | All | 0% | 11-4-26 | 11-10-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 11 13 F
29. Deployment | Ayush + Niharika | 0% | 11-6-26 | 11-11-26 | bar: Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S; Nov 4 6 F to Nov 11 11 W
30. Final Documentation / Project Report | All | 0% | 11-5-26 | 11-13-26 | bar: Aug 12 12 W to Aug 12 14 F; Aug 12 17 M to Aug 19 21 F; Aug 19 24 M to Aug 26 28 F; Aug 26 31 M to Sep 2 4 F; Sep 2 7 M to Sep 9 12 S; Sep 9 14 M to Sep 16 18 F; Sep 16 20 S to Sep 23 25 F; Sep 23 28 M to Sep 30 2 F; Sep 30 5 M to Oct 7 10 S; Oct 7 12 M to Oct 21 23 F; Oct 21 26 M to Oct 28 30 F; Oct 28 2 M to Nov 11 13 F
31. Final PPT & Viva Demonstration | All | 0% | 11-11-26 | 11-15-26 | bar: Sep 9 12 S; Sep 16 20 S; Oct 7 10 S; Oct 14 17 S to Oct 14 18 S; Nov 11 11 W to Nov 11 15 S